## Sheet1
Risk ID | Asset | Description | Likelihood | Impact | Severity | Mitigation | Owner
R-001 | phpMyAdmin | Local File Inclusion (CVE-2005-3299) via subform parameter in grab_globals.lib.php. | High | High | Critical | Disable/remove phpMyAdmin; patch; restrict file access. | Web App Administrator
R-002 | Login Page | Potential brute-force / credential-stuffing target. | Medium | High | High | Implement rate-limiting, captcha, account lockout. | Web App Developer
R-003 | Admin Panel (inferred) | Hidden or weakly protected entry point could allow privilege escalation. | Medium | High | High | Discover endpoints; enforce authentication and RBAC. | Security Analyst
R-004 | FTP Service | Outdated FTP service; risk of credential reuse or file manipulation. | High | Medium | High | Replace with SFTP; enforce strong auth; disable anonymous. | Network Admin
R-005 | Public Metadata | Outdated jQuery and exposed scripts increase XSS risk. | Medium | Medium | Medium | Update libraries, apply CSP headers, sanitize inputs. | Front-End Developer
R-006 | HTTP Proxy | Open or misconfigured HTTP proxy could enable MITM or cache poisoning. | Medium | High | High | Disable proxy or apply ACLs; validate headers. | Infrastructure Lead
R-007 | Port 25 (SMTP) | Filtered port may indicate misconfigured mail services. | Low | Medium | Low | Verify necessity; monitor logs; apply firewall rules. | Email Server Admin